## Slide 1: Big Pharma Company
Implementation plan for ChemBERTa

## Slide 2
Technical Requirements
Gather pre-training datasets
Resources to deploy the chemBerta model
Storage for training datasets (Azure Object storage/AWS S3)
Establish python model requirements (Example TensorFlow, pytorch)
Establish Linux based environments for deployment of the model
Automate deployment using Docker & Kubernetes
Setup deployment pipelines using Jenkins
Establish database to support the model ( Example Postgres)
Establish open-source software
Setup batch process pipelines using Airflow(open-source cyclic graphs)
Cost analysis of storage and compute

## Slide 3: Project implementation requirements
Teams would work in an agile format over the course of 9 months
3 months of initial POC and 6 months of development and release
6 months broken down into 2 PI’s (program increments)/3 months each
Each PI would be then broken into 6 sprints (2 weeks each)
Required teams:
2 Development teams
1 Deployment team
1 Release team
1 Testing Team

## Slide 4: Environment structure for developments process
Local environments
Dev: Env for all developers to contribute and component test (unstable Env)
QA: Integration testing Env (Semi stable Env)
UAT: E2E test and perform user acceptance testing (Pre-stable Env)
Stage: E2E testing and scale testing the applications (Stable Env)
Production: Stable Env for user interactions
Un-managed Environment for datasets(No client pre-training data)
Managed Environment for datasets(Client data for model training)

## Slide 5
Analysis
Development
Infra & Deployment
Testing
Today
Q1
Q2
Q3
Requirement gathering
Infrastructure analysis
Initial POC
Development cycle
Documentation
Phase 1
Phase 2
Phase 3
Documentation and approvals
Resourcing/Onboarding
Development cycle
V1 Development cycle
V2 Development cycle
V1 acceptance testing
DEV/QA Setup
DEV/QA Stabilize
UAT/STAGE/PROD
Setup
DEV/QA Deploy
Final PROD release
Upper Env’s Deployment
R1
Rn
POC testing
QA testing
Scale testing setup
Scale testing
Smoke test
Smoke test
Roadmap for development and Deployment

## Slide 6: Summary
As highlighted in the problem statement our goal is to implement ChemBerta training model in our current implementation.
We would need to run analysis on the current technology requirements as highlighted previously in the slides and setup infrastructure to support the implementation at scale.
We would then investigate resourcing which would leverage expertise from BPC and our team for effective and robust implementation.
After establishing the initial requirements, we would work in an agile project flow process to roll out the implementation with a consistent release cycle.